## Sheet2
MCI Project Weekly Time Sheet
Team | 22-N | Student ID | a1847791 |  |  | Week starting: | Feb 26 (Week 1)
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday
Tuesday
Wednesday | 2024-02-28 | 16:00 | 18:00 | 2 | Discuss with team members to submit our project preferences. | Submitting the project preferences on time to kickstart the project research as soon as possible. | Wait for Cruz's confirmation on the project result.
Thursday
Friday
Saturday
|  |  | Total | 2
MCI Project Weekly Time Sheet
Team | 22-N | Student ID | a1847791 |  |  | Week starting: | Mar 4 (Week 2)
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 2024-03-04 | 10:00 | 0:00 | 2 | Prepare what to discuss for tomorrow's internal meeting. | Sets up regular communication channel with team member sas early as possible. | Review project brief.
Tuesday | 2024-03-05 | 14:00 | 15:00 | 1 | Internal meeting: 1) Schedule weekly online group meetings. 2) Email client to introduce team and schedule first meeting. 3) Propose Discord for categorized discussions. 4) Create dedicated Google Drive for document sharing. | 1) Enhances team communication and coordination. 2) Establishes communication with client and kickstarts project. 3) Improves organization and efficiency in team communication. 4) Streamlines document management and collaboration within team. | 1) Set recurring meeting time and platform. 2) Await client response for meeting confirmation. 3) Discuss and implement Discord channels. 4) Share Drive link with team for access.
Wednesday | 2024-03-06 | 10:00 | 11:00 | 1 | 1) Answer client email. 2) Confirm client meeting time with team members. | Establishes communication with client. | Finalized the first client meeting is this Friday at 11 am via Zoom.
Thursday | 2024-03-07 | 10:00 | 13:00 | 3 | Internal meeting: 1) Create a client meeting host's and minute taker's roster. 2) Put down questions to ask client in the meeting agenda for tomorrow's client meeting. | Make sure the client meeting will run smoothily. | 1) Client meeting's roster is created and team members have filled it up. 2) I created the client meeting's agenda and minute templates in the shared Google Drive.
Friday | 2024-03-08 | 11:00 | 13:00 | 2 | Client meeting: 1) Meet with the client. 2) Ask the client about the project scope. 3) Meet with some team members after the client meeting to clarify what we've learned from the client. | Have more clarities about the main functions of the WellSpace website from the project brief. | 1) The main functions of the website includes basic landing page, educational content from the mental health experts, allowing users to post their discussions about the expert-led articles, and booking counselling sessions. 2) We can start search for ideas about how to implement them and prepare for more follow-up questons.
Saturday | 2024-03-09 | 10:00 | 18:00 | 8 | Search existing website as example. | Sets the benchmark for the website we're going to build. | Record the similar website structure and will use the observed common structure as guideline for the pitch.
|  |  | Total | 17
MCI Project Weekly Time Sheet
Team | 22-N | Student ID | a1847791 |  |  | Week starting: | Mar 11 (Week 3)
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 2024-03-11 | 13:00 | 13:30 | 0.5 | Prepare for tomorrow's internal meeting: Gather some ideas and do some research to better understand client expectations from the project brief. | Identifies gaps and areas needing clarification or improvement. | 1) Compile ideas and research findings. 2) List questions to address during the meeting.
Tuesday | 2024-03-12 | 14:00 | 16:00 | 2 | Internal meeting: 1) Discuss to allocate team members to frontend and backend roles. 2) Divide website functions for pitch presentation. | 1) Defines team responsibilities and aligns with project objectives. 2) Begins focused work on key aspects of the project. | 1) Assign roles based on skills and preferences. 2) Outline tasks for each function and start work.
Wednesday | 2024-03-13 | 10:00 | 18:00 | 8 | 1) Post question on MyUni about main focus of pitch presentation. 2) Email client summarizing main website functions and preparation. 3) Start to search for backend related learning resources e.g. database. | 1) Gathers input and ensures alignment with project objectives. 2) Ensures client understanding and aligns team efforts for client meeting. | 1) Monitor responses and incorporate feedback. 2) Await client response and adjust presentation accordingly.
Thursday | 2024-03-14 | 10:00 | 19:00 | 9 | 1) Internal meeting: Finalize our draft pitch presentation for tomorrow's client meeting. 2) Search for backend related learning resources e.g. Express.js and Node.js | Ensures readiness and professionalism for client interaction. | Review and polish presentation for tomorrow.
Friday | 2024-03-15 | 9:00 | 11:30 | 2.5 | Client meeting - I'm the host for today's client meeting, so I 1) Host client meeting, adding slides and discussing details. 2) Present follow-up questions on Events, Discussion, and User authentication. | 1) Enhances client understanding and engagement. 2) Clarifies project requirements and gathers client feedback. | Document client responses and adjust project plan.
Saturday | 2024-03-16 | 13:00 | 21:00 | 8 | 1) Internal meeting: Discuss our draft pitch presentation. 2) Add sitemap to pitch presentation. | Ensures alignment with project goals and refines presentation. | Identify areas for improvement and make revisions.
|  |  | Total | 30
MCI Project Weekly Time Sheet
Team | 22-N | Student ID | a1847791 |  |  | Week starting: | Mar 18 (Week 4)
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday |  |  |  |  | 1) Search for backend related learning resources e.g. Schema and UML relationships. 2) Finalize my part of the pitch presentation (adding the sitemap to the pitch presentation).
Tuesday
Wednesday
Thursday
Friday
Saturday
|  |  | Total | 0
MCI Project Weekly Time Sheet
Team | 22-N | Student ID | a1847791 |  |  | Week starting: | Mar 25 (Week 5)
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday
Tuesday
Wednesday
Thursday
Friday
Saturday
|  |  | Total | 0
MCI Project Weekly Time Sheet
Team | 22-N | Student ID | a1847791 |  |  | Week starting: | Apr 1 (Week 6)
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday
Tuesday
Wednesday
Thursday
Friday
Saturday
|  |  | Total | 0
MCI Project Weekly Time Sheet
Team | 22-N | Student ID | a1847791 |  |  | Week starting: | Apr 8 (Week 7)
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday
Tuesday
Wednesday
Thursday
Friday
Saturday
|  |  | Total | 0
MCI Project Weekly Time Sheet
Team | 22-N | Student ID | a1847791 |  |  | Week starting: | Apr 15 (Week 8)
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday
Tuesday
Wednesday
Thursday
Friday
Saturday
|  |  | Total | 0
MCI Project Weekly Time Sheet
Team | 22-N | Student ID | a1847791 |  |  | Week starting: | Apr 22 (Week 9)
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday
Tuesday
Wednesday
Thursday
Friday
Saturday
|  |  | Total | 0
MCI Project Weekly Time Sheet
Team | 22-N | Student ID | a1847791 |  |  | Week starting: | Apr 29 (Week 10)
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday
Tuesday
Wednesday
Thursday
Friday
Saturday
|  |  | Total | 0
MCI Project Weekly Time Sheet
Team | 22-N | Student ID | a1847791 |  |  | Week starting: | May 6 (Week 11)
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday
Tuesday
Wednesday
Thursday
Friday
Saturday
|  |  | Total | 0
MCI Project Weekly Time Sheet
Team | 22-N | Student ID | a1847791 |  |  | Week starting: | May 13 (Week 12)
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday
Tuesday
Wednesday
Thursday
Friday
Saturday
|  |  | Total | 0
MCI Project Weekly Time Sheet
Team | 22-N | Student ID | a1847791 |  |  | Week starting: | May 20 (Week 13)
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday
Tuesday
Wednesday
Thursday
Friday
Saturday
|  |  | Total | 0
MCI Project Weekly Time Sheet
Team | 22-N | Student ID | a1847791 |  |  | Week starting: | May 27 (Week 14)
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday
Tuesday
Wednesday
Thursday
Friday
Saturday
|  |  | Total | 0
MCI Project Weekly Time Sheet
Team | 22-N | Student ID | a1847791 |  |  | Week starting: | Jun 3 (Week 15)
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday
Tuesday
Wednesday
Thursday
Friday
Saturday
|  |  | Total | 0
MCI Project Weekly Time Sheet
Team | 22-N | Student ID | a1847791 |  |  | Week starting: | Jun 10 (Week 16)
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday
Tuesday
Wednesday
Thursday
Friday
Saturday
|  |  | Total | 0