## Sheet2
MCI Project Weekly Time Sheet
Team | 22-N | Student ID | a1872641 | Siyu Ni |  | Week starting: | 26 Feb (week 1)
Day | Date | Time In | Time Out | Total hours | Task | How does it fit into project plan? | Outcome/Next action
Monday | 2024-02-26 |  |  | 0 | NA | NA | NA
Tuesday | 2024-02-27 |  |  | 0 | NA | NA | NA
Wednesday | 2024-02-28 | 8:00 | 10:00 | 4 | Meet with our new team members during the lecture and make sure to discuss our project preferences in the workshop. It is crucial that we do not procrastinate on this matter. | Project preferences would be submitted immediately to initiate research without any delay. | Wait for the project result.
Thursday | 2024-02-29 |  |  | 0 | NA | NA | NA
Friday | 2024-03-01 |  |  | 0 | NA | NA | NA
Saturday | 2024-03-02 |  |  | 0 | NA | NA | NA
|  |  | Total | 4
MCI Project Weekly Time Sheet
Team | 22-N | Student ID | a1872641 | Siyu Ni |  | Week starting: | 4 Mar (week 2)
Day | Date | Time In | Time Out | Total hours | Task | How does it fit into project plan? | Outcome/Next action
Monday | 2024-03-04 | 10:00 | 13:00 | 3 | Research and gather resources for Backend API development for quiz page and function discussion | Developing robust quiz functionalities to engage users and gather data for analytics. | Drafted initial API endpoints; set up meeting for technical review.
Tuesday | 2024-03-05 | 10:00 | 12:00 | 2 | Attend feature discussion. | Task and function discuss | initial assign
Wednesday | 2024-03-06 | 15:00 | 17:00 | 2 | Discussion of functions | Furthur discussion | Better view of the whole project,start building API locally.
Thursday | 2024-03-07 | 17:00 PM | 20:00 PM | 3 | Backend API researching and learning. | Researching the integration of backend API with frontend components. | Prepare for possible obstacles; prepare for round of user acceptance.
Friday | 2024-03-08 | 10:00 | 12:00 | 2 | Client meeting | Reviewing project progress with the client to ensure requirements are being met. | Positive client feedback received; to incorporate additional client suggestions
Saturday | 2024-03-09 | 9:00 | 17:00 PM | 8 | Project research Contribution,researching video merging technology | Prepare for business presentation | Finished PPT draft.
|  |  | Total | 20
MCI Project Weekly Time Sheet
Team | 22-N | Student ID | a1872641 | Siyu Ni |  | Week starting: | 11 Mar (week 3)
Day | Date | Time In | Time Out | Total hours | Task | How does it fit into project plan? | Outcome/Next action
Monday | 2024-03-11 | 10:00 | 16:00 | 6 | Research on advanced API security protocols and Backend architecture refinement. | Ensuring the WellSpace platform adheres to the latest security standards for user data protection.Enhancing system architecture for future feature scalability and maintenance. | Refined system architecture diagrams; to discuss with the team in the next meeting.
Tuesday | 2024-03-12 | 11:00 | 17:00 | 6 | Collaborate with design team to refine API according to UX feedback. | Refinement based on UX input to ensure APIs provide data in a user-friendly way. | APIs updated; ready for front-end consumption.
Wednesday | 2024-03-13 | 9:00 | 12:00 | 3 | Attend weekly lecture, participate in workshop, and backend API schema design. | Ensuring API design meets both educational insights and functional requirements. | Schema drafted; review and implement best practices learned from lecture.
Thursday | 2024-03-14 | 10:00 | 17:00 | 6 | Backend system architecture optimization for improved API response times. | Optimizing backend for scalability and efficiency in preparation for user growth. | Identified bottlenecks; improved system performance.
Friday | 2024-03-15 | 10:00 | 15:00 | 5 | Weekly client meeting and strategic planning for next API development phase. | Aligning client expectations with project roadmap to set clear goals for API features. | Received client input; scheduled development tasks for upcoming week.
Saturday | 2024-03-16 |  |  |  | NA | NA | NA
|  |  | Total | 26
MCI Project Weekly Time Sheet
Team | 22-N | Student ID | a1872641 | Siyu Ni |  | Week starting: | 18 Mar (week 4)
Day | Date | Time In | Time Out | Total hours | Task | How does it fit into project plan? | Outcome/Next action
Monday | 2024-03-18 | 9:00 | 12:00 | 3 | Design and develop backend data models for the quiz and information pages. | Creating robust data models is crucial for the scalability and maintainability of the API. | Data researching completed; prepare for review with the data team.
Tuesday | 2024-03-19 | 10:00 | 15:00 | 5 | Implementing new authentication features for API security. | Strengthening security to ensure safe user data handling and compliance with regulations. | Authentication layer enhanced; plan for security audit.
Wednesday | 2024-03-20 | 9:00 | 14:00 PM | 5 | Apply insights from the lecture to API development and participate in collaboration workshop. | Integration of new knowledge ensures API is built with best practices. | Updated API with new features; schedule testing for the following week.
Thursday | 2024-03-21 | 10:00 | 17:00 | 7 | Backend development work focused on improving the efficiency of the database queries. | Efficient queries are essential for a responsive API as user load increases. | Database queries optimized; monitor for performance improvements.
Friday | 2024-03-22 | 10:00 | 14:00 | 4 | Client meeting to discuss project progress and next steps. | Keeping the client informed ensures that the project remains aligned with their vision. | Client feedback received; incorporate changes into next sprint.
Saturday | 2024-03-23 |  |  |  | NA | NA | NA
|  |  | Total | 24
MCI Project Weekly Time Sheet
Team | 22-N | Student ID | a1872641 | Siyu Ni |  | Week starting: | 25 Mar (week 5)
Day | Date | Time In | Time Out | Total hours | Task | How does it fit into project plan? | Outcome/Next action
Monday | 2024-03-25 | 9:00 | 17:00 | 8 | Building out RESTful API endpoints for new content management functionalities. | New API endpoints will allow for dynamic content updates, enhancing the site’s manageability. | Completed API endpoints for content management; prepare for integration testing with frontend.
Tuesday | 2024-03-26 | 9:00 | 12:00 | 3 | Optimizing API caching mechanisms to improve data retrieval times. | Effective caching is vital for high-performing APIs, especially with increasing user traffic. | Implemented caching; monitor API response times and adjust as necessary.
Wednesday | 2024-03-27 | 9:00 | 18:00 PM | 4 | Incorporate lecture learning into API development, participate in cross-functional workshop. | Leveraging new learning to keep API at cutting-edge and facilitate team-wide knowledge sharing. | API updated with new security features; organize a team debrief.
Thursday | 2024-03-28
Friday | 2024-03-29
Saturday | 2024-03-30 | 10:00 | 15:00 | 5 | Refining API documentation for end-users and developers. | Clear documentation is essential for user adoption and developer onboarding. | Enhanced API documentation; schedule review with technical writing team.
|  |  | Total | 20
MCI Project Weekly Time Sheet
Team | 22-N | Student ID | a1872641 | Siyu Ni |  | Week starting: | 1 Apr (week 5)
Day | Date | Time In | Time Out | Total hours | Task | How does it fit into project plan? | Outcome/Next action
Monday | 2024-04-01 | 9:00 | 17:00 | 8 | Code refactoring for the API based on feedback from the client and frontend team. | Refactoring improves code quality and API maintenance for long-term project health. | Refactoring completed; set up a code review session.
Tuesday | 2024-04-02
Wednesday | 2024-04-03 | 9:00 | 18:00 | 3 | Applying advanced database indexing strategies learned from lecture to improve API efficiency. | Advanced indexing is crucial for optimizing database searches and API performance. | Database optimization complete; monitor for improved performance metrics.
Thursday | 2024-04-04
Friday | 2024-04-05 | 10:00 | 15:00 | 5 | Final client meeting to demonstrate API capabilities and discuss | Confirming the API meets all requirements and is ready for launch aligns with the project timeline. | Client confirmed readiness for launch; schedule deployment.
Saturday | 2024-04-06 | 10:00 | 15:00 | 5 | Preparing for deployment, final checks, and team coordination. | Ensuring all systems are go for deployment to avoid issues during launch. | Deployment checklist completed; ready for launch.
|  |  | Total | 21